## Read me
UAT checklist
Start here | Use Blank template for your work. Completed example contains fictional Northstar Shop data; do not paste it into your live results.
Editing | All cells are editable. Replace the project line. Use one row per item; keep IDs stable. Wrap text is on. Increase row height for longer entries.
Dropdowns | Use the selection lists in Status. Blank cells are allowed. In Excel, invalid typed choices show an error.
Filtering | Use the arrows in row 5 to filter and sort the whole table. The header and first two columns stay visible as you scroll.
More rows | 12 working rows are provided. If you add rows, copy a working row to preserve dropdowns, extend the table, and update the print area.
Printing | Data sheets use A3 landscape, one page wide, with repeating headers. Use A3 paper or export to PDF at A3. For A4, select fewer columns or print individual reports; do not shrink all columns to A4.
Compatibility | These are .xlsx workbooks, not legacy .xls files or hosted Google Sheets copies. Import behavior varies by app; check dropdowns and print settings after import.
Using the checklist | Checkpoint prompts are supplied on the blank sheet; status, owner, date and evidence are empty. Assign an owner to each. Done needs evidence; N/A needs a reason. Review blocked items before sign-off.
Source | Free to copy and adapt / ybug.io. All names, domains, evidence files and approvals in the examples are fictional.

## Blank template
UAT checklist / Blank template
Enter your own data below. Dropdowns are available in the labeled columns.
Project: ____________________ Build / run: ____________________ Owner: ____________________
Phase | Checkpoint | Status | Owner | Reviewed on | Evidence / exceptions
Prepare | Scope and entry/exit criteria approved
Prepare | Staging build and payment sandbox available
Prepare | Synthetic data, stock and test inbox ready
Prepare | Desktop and mobile testers have access
Prepare | Cases linked to requirements; defect process agreed
Execute | Every planned case run; results and evidence recorded
Execute | Critical and major defects fixed and retested
Execute | Required mobile checks completed
Close | Exceptions reviewed with owner and due date
Close | Final results match sign-off summary
Close | Business and QA approvals recorded
Close | Deployment owner and smoke test confirmed

## Completed example
UAT checklist / Completed example
Fictional completed run; compare with the blank sheet.
Northstar Shop / checkout release 2.4 / final review September 11, 2026 / Maya Chen
Phase | Checkpoint | Status | Owner | Reviewed on | Evidence / exceptions
Prepare | Scope and entry/exit criteria approved | Done | Alex | 2026-09-08 | Plan approved Sep 8; checkout requirements v3.
Prepare | Staging build and payment sandbox available | Done | Sam | 2026-09-08 | rc1 smoke checks passed Sep 8.
Prepare | Synthetic data, stock and test inbox ready | Done | Maya | 2026-09-08 | Trail Mug, SAVE10 and sandbox mailbox reset.
Prepare | Desktop and mobile testers have access | Done | Maya | 2026-09-08 | Maya and Alex confirmed access Sep 8.
Prepare | Cases linked to requirements; defect process agreed | Done | Maya | 2026-09-08 | UAT-001 to 006; BUG log reviewed with Sam.
Execute | Every planned case run; results and evidence recorded | Done | Maya | 2026-09-11 | 6 of 6 cases executed on rc2.
Execute | Critical and major defects fixed and retested | Done | Maya | 2026-09-11 | BUG-014 and BUG-015 verified on rc2.
Execute | Required mobile checks completed | Done | Alex | 2026-09-11 | UAT-005 and 006 passed on iPhone 13.
Close | Exceptions reviewed with owner and due date | Done | Alex | 2026-09-11 | No open exceptions at final review.
Close | Final results match sign-off summary | Done | Maya | 2026-09-11 | 6 pass / 0 fail / 0 blocked / 0 not run.
Close | Business and QA approvals recorded | Done | Alex | 2026-09-11 | Both approvals recorded Sep 11.
Close | Deployment owner and smoke test confirmed | Done | Sam | 2026-09-11 | Sam owns Sep 14 deployment and checkout smoke test.